# EMLS Pilot Plan

Example 6-month pilot pathway for institutional partners

EduLinked Pty Ltd | Contact: founder@edulinked.com.au

Source page: www.edulinked.com.au/projects/emls/

This document is written in plain language and is intended for institutional enquiry, pilot planning and accessible procurement conversations.

# 1. Purpose of a pilot

An EMLS pilot helps an institution test selected modules, accessibility variants, facilitator workflows and reporting outputs before a broader deployment decision.

# 2. Pilot phases

| Item | Details |
| --- | --- |
| Phase 1 - Scope | Confirm partner goals, target learners, delivery sites, access needs, governance requirements and reporting requirements. |
| Phase 2 - Select modules | Choose one or more modules and confirm whether adaptations are needed for the local setting. |
| Phase 3 - Configure | Prepare lesson sequences, Easy Read resources, captioned media references, Auslan-ready summaries and facilitator materials. |
| Phase 4 - Train facilitators | Provide practical orientation and facilitator guidance. |
| Phase 5 - Deliver and verify | Run sessions, collect evidence, record accessibility uptake and support reporting. |
| Phase 6 - Evaluate and scale | Review learner outcomes, facilitator experience, time saved, access uptake and partner satisfaction. |

# 3. Suggested pilot timeline

| Item | Details |
| --- | --- |
| Month 0 | Onboarding and accessibility planning. |
| Months 1-2 | Configuration and facilitator training. |
| Months 3-4 | Pilot delivery and evidence collection. |
| Months 5-6 | Evaluation, reporting and scale decision. |

# 4. Information needed from a partner

Which learner groups or sites may be involved.

Which modules or learning goals are most relevant.

What accessibility formats are required.

Who will facilitate the sessions.

What reporting or governance evidence is required.

Whether the partner is exploring a pilot only or a future licensing pathway.

# 5. Pilot success measures

Learner confidence or participation change.

Facilitator preparation time saved.

Use of accessible variants such as Easy Read, captions or symbol support.

Quality of evidence collected for reporting.

Partner satisfaction and readiness to continue.

No guarantee statement: EMLS supports inclusive learning, accessible delivery and evidence-informed reporting. It does not guarantee procurement approval, funding approval, licensing approval, learner outcomes, formal accreditation or institution-wide adoption unless separately agreed in writing.